## Slide 1: Platform Study Monitoring
The experience
Gail Owen, Clinical Trial Manager
Enroll-HD Congress, Quebec 2018

## Slide 2: Study Overview
HDClarity is a multi-site CSF and plasma collection
  currently active in Canada, US, UK and Germany
  sites planned in Spain, Italy, Poland, Portugal, France
Minimum of 2 study visits, screening and sampling
  20ml CSF and up to 50ml plasma are collected
Potential for repeat sampling visits
The HDClarity PI is not necessarily the Enroll-HD PI

## Slide 3
Enroll-HD is the platform for HDClarity
Sites and participants must be active in Enroll-HD
Linked EDC used for HDClarity data capture
Enroll-HD core assessments are repeated at HDClarity screening if >2 months since Enroll-HD visit
Enroll-HD General Forms are updated at all visits

## Slide 4: HDClarity EDC
General Forms are visible and able to enter data at every visit and every study
When Enroll-HD visit has not occurred within 60 days of HDClarity Screening then the Enroll core assessments are repeated during screening
HDClarity Screening
HDClarity Sampling

## Slide 5: Site set up and training

## Slide 6: Site selection
The Enroll-HD team advise on site selection based on
  known expertise and clinical trial experience
  performance in Enroll-HD (recruitment, site issues, PVs, data entry)
  participant population
A site selection questionnaire then determines if the site
  is able to deliver the protocol (e.g. rapid sample processing)
  has access to the necessary equipment (-80 freezer, 2 centrifuges)
  has access to a certified lab able to perform CSF cell counts

## Slide 7: Site set up
When an approved ICF and site agreement are in place, HDClarity CC collect
  PI signed protocol
  PI signed delegation log
  CVs and GCP for everyone on the delegation log
  User Roles and Responsibilities Form (URRF) for EDC access
  Calibration certificates for pipettes, centrifuges and freezer
The HDClarity delegation log is checked with the Enroll-HD team to ensure that all raters are appropriately certified
HDClarity CC collect medical license registration information for all clinicians that are not already in Enroll-HD

## Slide 8: Site initiation
Prior to the site initiation visit (SIV), the site are given access to the HDClarity training videos on the EDC
A study-specific investigator site file is provided
The first biosample kits are provided
The SIV is usually done remotely and consists of 2 parts
  The technical SIV (sample collection and processing)
  The non-technical SIV (e.g. recruitment, scheduling, EDC training, participant and site payment)
Following the SIV, the site complete the HDClarity training log and are given access to the EDC training site

## Slide 9: study execution

## Slide 10: Inclusion criteria
Group | Local CAG | Disease Burden | UHDRS Diagnostic Confidence | UHDRS TFC
Control | <36 (or no known family history) | - | - | -
Early Premanifest | ≥ 40 | < 250 | < 4 | -
Late Premanifest | ≥ 40 | ≥ 250 | < 4 | -
Early Manifest | ≥ 36 | - | 4 | 7-13
Moderate Manifest | ≥ 36 | - | 4 | 4-6
Late Manifest | ≥ 36 | - | 4 | 0-3

## Slide 11: Inclusion criteria
Group | Local CAG | Disease Burden | UHDRS Diagnostic Confidence | UHDRS TFC
Control | <36 (or no known family history) | - | - | -
Early Premanifest | ≥ 40 | < 250 | < 4 | -
Late Premanifest | ≥ 40 | ≥ 250 | < 4 | -
Early Manifest | ≥ 40 | - | 4 | 7-13
Moderate Manifest | ≥ 40 | - | 4 | 4-6
Late Manifest | ≥ 40 | - | 4 | 0-3

## Slide 12: Inclusion criteria
If there’s no local CAG available or the report does not contain allele lengths, sites must confirm eligibility with HDClarity CC
Genotype unknown are not eligibile
Community controls are eligible

## Slide 13: Visit frequency
Sampling
Optional repeat sampling
Screening
-30 days
0
+56
+28
Up to 3 visits within 4-8 weeks

## Slide 14: Definitions for reportable events
AEs must be reported within 48 hours using the HDClarity specific AE log
  Verbatim term describing the event (Medra)
  Date of event
  Severity
  Relationship to Study
  Final outcome
  Expected

## Slide 15: Definitions for reportable events
SAEs must be reported within 24 hours using the SAE eCRF
  Brief description of the SAE
  Category
  Any medical, behavioural, or other intervention taken as a result of this SAE
  Final outcome
  Status of the SAE report

## Slide 16: Study specific waivers
More than 60 days between the last Enroll-HD visit and the HDClarity Screening visit
More than 30 days between the HDClarity Screening and HDClarity Sampling Visits
Any variations to the Inclusion and/or Exclusion criteria including screening safety bloods out of range
In addition, CI approval is required in advance for rescreening

## Slide 17: Cross-site enrollment

## Slide 18: Monitoring

## Slide 19: IMV scheduling
HDClarity IMVs are performed alongside an Enroll-HD IMV
HDClarity Clinical Site Status Tracker is circulated weekly
  Current recruitment
  Site status (in set-up, open to recruitment)
Enroll-HD inform HDClarity CC of the planned IMV scheduling
The date of the RDR tracker request is provided
Time allocated depends on the number of eligible visits

## Slide 20: During the IMV
Review of informed consent forms
Verify eligibility of enrolled participants
Review HDClarity ERB/ REB/ IRB approval of revisions to ICF
Check status of required revisions noted during previous IMV
Continued adequacy of study staff and facilities for HDClarity
Review of new and ongoing AEs and SAEs
Protocol violations
Inspect ISF
Equipment
Source data verification

## Slide 21
Source Data Verification
Screening visit SDV
  100% for ICFs, inc/exc criteria, waivers, AEs
  50% for screening safety blood reports
  25% for Concomitant medications and comorbid conditions
  10% for Enroll-HD core assessments completed at screening
Sampling visit
  100% eligibility check, waivers, AEs
  50% for CSF and blood collection and processing and CSF cell counts
  25% for Concomitant medications and comorbid conditions

## Slide 22: ICFs
As a minimum requirement, ICF checks must be complete before samples can be shared
HDClarity shipment page now includes a notification that ICF has been checked off
HDClarity ICF monitoring form in development

## Slide 23: Working with central laboratories
Laboratory staff are often not part of the clinical site team under the direction of the site PI
Central or external labs have local SOPs for sample processing
Only the lab manager may be named on the delegation log and is responsible for ensuring lab staff are trained on the study protocol
Paper forms and worksheets are provided
  Biosample processing kits are mixed
  Implausible processing times
  Number of samples implausible or incorrectly recorded
  Time of storage

## Slide 24
Screening safety bloods

## Slide 25: CSF cell counts

## Slide 26: Protocol violations
Ahead of the IMV, the HDClarity PV tracker is provided
  Informed consent
  Data protection
  Inc/exc criteria
  Biosamples (CSF or blood volume, samples stored incorrectly)
  Safety (unreported S/AE, LP when safety bloods out of range)
  Other
Few PVs but most common are informed consent, CAG ineligibility, blood volume >50ml and AE reported >48 hours
Need to be informed of any Enroll-HD PVs that may necessitate quarantine of HDClarity data

## Slide 27: IMV Reporting
A separate report template for each platform study
IMV follow up letter sent to site and HDClarity CC
IMV report and PV tracker sent to HDClarity CC

## Slide 28: Acknowledgements
Ed Wild, Stef Gosling, Filipe Brogueira Rodrigues
Elena Pak, Dipinder Kaur, Jamie Levey, Sherry Lifer, Rebecca Rocha, Dave Rankin, Robi Blumenstein
UCL
HDClarity
Eileen Neacy, Olivia Handley, Torsten Illmann & team, Selene Capodarca, Shilpa Deshpande, Jenny Townhill, Jenny Callaghan, Language Coordinators and CRAs
Enroll-HD & EHDN